## Sheet2 (hidden)
Anguilla
Antigua & Barbuda
The Bahamas
Barbados
Belize
Bermuda
British Virgin islands
Cayman Islands
Dominica
Grenada
Guyana
Haiti
Jamaica
Montserrat
St. Kitts & Nevis
St. Lucia
St. Vincent & the Grenadines
Suriname
Trinidad & Tobago
Turks & Caicos Islands

## Workplan FY16-REVISED (hidden)
Work Plan (May 2015 to April 2016): Macroeconomics Programming and Analysis
TA Area | Medium-Term Outcome in the Log Frame | Country | Activity: May 2015 - April 2016 | Inputs: May 2015 - April 2016 (in person-weeks) |  |  |  | Updated Inputs at Nov 1, 2016 (person-weeks - changes in red) |  |  |  | % of updated plan delivered at end-Oct | Delivery status | Milestones | Comments
|  |  |  | IMF HQ | CARTAC resident advisors | ST experts | Total | Updated IMF HQ | Updated LTX | Updated STX | Updated Total
Macroeconomic analysis | Outcomes 1-4 | ECCU | Workshop to assist ECCU Macro Policy Units produce an internally consistent set of macro/fiscal projections | 0.1 | 2 | 2 | 4.1 | 1 | 2 | 2 | 5 | 100 | Delivered on May 6-15 May. | All countries producing internally consistent debt projections | Covered cost for WHD Economist to present over two days
|  | Regional | ICD Course on Macroeconomic Diagnostics | 3 | 1 | 0 | 4 | 3 | 1 | 0 | 4 | 0 | Scheduled for March 14-18 in Suriname. | Workshop deliver on global best practice macro surveillance | Topic changed to Macroeconomic Forecasting. Venue and dates confirmed. | Will happen
| 1. Countries are using macroeconomic forecasts as a basis for annual and medium-term budgets (PI 14(ii), FTE 2.1.2) | SVG | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 2 | 0 | 2.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled. Reduced by 1 week. | Macro Policy Unit independently producing forecasts |  | May happen
|  | Dominica | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 100 | Delivered 28 September - 4 October | Macro Policy Unit independently producing forecasts | The one week Fund staff visit is replaced by this mission
|  | Saint Lucia | Review forecasting framework from previous training session | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 2 | 3.1 | 0 | Not yet scheduled. | Scenarios and risks surrounding baseline forecasts are produced | Mission title will change to assist with producing manuals for Macro Policy Unit | Delete
|  | Grenada | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 2 | 0 | 2.1 | 100 | Delivered July 13-17 | Macro Policy Unit independently producing forecasts | Successful mission so unplanned follow up mission added
|  | Trinidad & Tobago | Advise Ministry of Finance on GDP forecasting methodologies and then assist with implementation | 0.1 | 2 | 3 | 5.1 | 0.1 | 2.5 | 3 | 5.6 | 0.32609 | Delivered as part of IMF mission: Sept 15-25, remainder to be delivered in H2 | MoF of T&T producing multi-year projections with detailed scenarios |  | Should happen
|  | St Kitts | Assist MoF with GDP projection frameworks | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Scheduled Feb 22-26 | Fiscal unit internally producing Macro projections |  | Will happen
|  | Anguilla | Follow up mission to assist with medium-term GDP projections | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled. | producing scenarios around baseline projections |  | Complete
|  | Barbados | Training MoF staff in techniques of Macro projections | 0.1 | 2 | 2 | 4.1 | 0.1 | 1 | 0 | 1.1 | 0.45455 | 2 half days delivered on October 15 and October 20. Fiscal rules mission to occur on Nov-4-16 | MoF undertaking GDP projections | Delivered 2 half days of assistance to MoF. Barbados fiscal rules mission allocated to this. STX have been removed | LTX yes, STX MAYBE
|  | Antigua | Assist with real sector analysis and projections (joint with PFM) | 0.1 | 1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | Cancelled: No commitment from authorities | MoF undertaking GDP projections
| 2. Countries annual budgetary process underpinned by a medium-term macro framework (PI 14(i), FTE 2.1.3) | Turks and Caicos | Follow up revenue forecasting workshop to produce final multi-year projections along with beginning training on MTFF | 0.1 | 0 | 1 | 1.1 | 0.1 | 0 | 1 | 1.1 | 0 | Not yet scheduled | SPDD producing multi-year revenue projections | Leaning on cancelling unless hear back from authorities soon | CANCELLED
|  | Bahamas | Introductory visit and assistance with revenue forecasting | 0.1 | 0 | 1 | 1.1 | 0 | 0 | 0 | 0 | 0 | Cancelled: No commitment from authorities | Revenue forecasts underpinned by macro inputs | Multiple emails sent to FS with no response.
|  | Dominica | Follow up mission to assist with medium-term fiscal framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Policy unit operating sound internally consistent macroeconomic framework |  | Should happen
|  | SVG | Assist team in the refinement of MTFF | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Internally consistent MTFF |  | Should happen
|  | Barbados | Training MoF staff in techniques of revenue projections | 0.1 | 0 | 2 | 2.1 | 0.1 | 0 | 2 | 2.1 | 0 | Not yet scheduled | Revenue projections based on sound Macro inputs |  | May happen
|  | Guyana | Developing a medium-term framework |  |  |  | 0 | 0.1 | 3 | 2 | 5.1 | 9.8039 | Week 1 Scheduled for 16-20 November, 2 further weeks planned but unscheduled | Improved medium-term framework | This unplanned mission was born out of the election | LTX yes, STX MAYBE
|  | Regional | Revenue forecasting and tax policy modelling workshop |  |  |  |  | 3 | 1 | 0 | 4 | 0 | Aiming for late April | Improved medium-term framework | FAD workshop, previously not programmed | Moved to next FY
| 3. Countries adequately reporting on macroeconomic risks and policy (PI 5) | Regional | Workshop - medium term economic and fiscal outlook statements (jointly with CARTAC PFM) | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 100 | Delivered in July | Workshop delivered. Action Plans to implement workshop learnings produced.
|  | Regional | Joint workshop with FS (Shelton) on Macro-Financial linkages | 0.1 | 1 | 1 | 2.1 | [5 empty] | Unscheduled | Modelling capacity built for central bankers to better monitor macro risks to the economy | To discuss with David, Budget dependent
|  | Dominica | Assist with economic reporting | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Further reporting on macroeconomic events |  | Should happen
|  | Saint Lucia | Improving research capacity | 0.1 | 1 | 2 | 3.1 | 0.1 | 1 | 2 | 3.1 | 0 | Scheduled Jan 11-15 | Policy and research papers produced | STX will be Winston Moore | May happen
| 4. Improved macroeconomic and fiscal coordination | Barbados | Provide advice on setting up a macro policy unit | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Scheduled November 4-16 | Policy unit set up | Rolled into FAD fiscal rules mission | Complete
|  | Regional | Workshop for Financial Secretaries (jointly with CARTAC PFM) | 0.1 | 1 | 0 | 1.1 | [5 empty] | Cancelled due to shifting prioties, another regional workshop added. | Workshop delivered. Action Plans to implement workshop learnings produced.
|  |  |  | 5.1 | 23 | 14 | 42.1
|  |  | Original Plan: | 5.1 | 23 | 14 | 42.1
|  |  | Updated Plan at Nov 1: |  |  |  |  | 8.7 | 23.5 | 14 | 46.2
Delivered at Nov 1:
Percentage of Original Plan:
Percentage of Adjusted Plan:

## Fin Sector Supervision
FY18 Work Plan - May 2017 to April 2018: Financial Sector Supervision (FSS)
TA Area | Objective | Country | Outcome Targeted | Activity | May 2017 - April 2018 |  |  | Number of Missions/ Activities | Milestones | Comments | Planned Date | Experts
(in person-days)
[5 empty] | PFTAC resident advisors | ST experts | Total
Financial Sector Supervision | 1. Develop and strengthen banking regulations in line with international standards | Cook Islands | 1.1 Supervisors and regulations require banks to apply sound policies and processes to identify, measure, monitor and control their financial risks on a timely basis and assess their capital adequacy in relation to their risk profile | RBS framework enhancement program. First follow-up mission. Develop a comprehensive suite of prudential statements. | 7 | 16 | 23 | 1 | i) Applicable guidelines and regulations are drafted by April 2018 ii) Applicable guidelines and regulations are finalized and formally issued. April 2019 | RBS enhancement program was initiated in FY2017. The program will provide technical assistance in key components of RBS framework – regulations; risk identification and assessment; risk rating; and supervisory action planning. | June 2017 | Stefanou/ Expert
|  |  | 1.2 Supervisors and regulations require banks to have robust governance policies and processes covering among others effective board and senior management oversight and sound control environment. | [5 empty] | i) Applicable guidelines and regulations are drafted by April 2018 ii) Applicable guidelines and regulations are finalized and formally issued. April 2019
|  | Fiji | 1.1 Supervisors and regulations require banks to apply sound policies and processes to identify, measure, monitor and control their financial risks on a timely basis and assess their capital adequacy in relation to their risk profile | Assistance with finalizing draft Credit Union legislation and by-laws | 0 | 12 | 12 | 1 | i) Credit Union legislation and by-laws finalized and issued. April 2019 | Continuation of work on developing credit union supervision undertaken by PFTAC with the RBF. | April 2018 | Expert
|  | FSM | 1.1 Supervisors and regulations require banks to apply sound policies and processes to identify, measure, monitor and control their financial risks on a timely basis and assess their capital adequacy in relation to their risk profile | Follow-up mission from the Regional Workshop on Banking Legislation and Prudential Standards | 5 | 12 | 17 | 1 | i) Applicable guidelines and regulations are drafted. April 2018 | Workshop to review and establish revision plan for banking legislation and prudential standards, to be held in July 2017. Followed up with bilateral missions to each country to follow-up on and progress reform. First follow-up. | February 2018 | Stefanou/ Expert
|  |  | 1.2 Supervisors and regulations require banks to have robust governance policies and processes covering among others effective board and senior management oversight and sound control environment. | [5 empty] | i) Applicable guidelines and regulations are drafted. April 2018
|  | Kiribati | 1.1 Supervisors and regulations require banks to apply sound policies and processes to identify, measure, monitor and control their financial risks on a timely basis and assess their capital adequacy in relation to their risk profile | Assistance with developing credit union supervision | 0 | 16 | 16 | 1 | i) Credit union supervision training delivered to supervisors ii) Supervision development and TA plan established | Continuation of work on developing credit union supervision undertaken by PFTAC. | August 2017 | Expert
|  | Palau | 1.1 Supervisors and regulations require banks to apply sound policies and processes to identify, measure, monitor and control their financial risks on a timely basis and assess their capital adequacy in relation to their risk profile | Follow-up mission from the Regional Workshop on Banking Legislation and Prudential Standards | 5 | 12 | 17 | 1 | i) Applicable guidelines and regulations are drafted. April 2018 | Workshop to review and establish revision plan for banking legislation and prudential standards, to be held in July 2017. Followed up with bilateral missions to each country to follow-up on and progress reform. First follow-up. | February 2018 | Stefanou/ Expert
|  |  | 1.2 Supervisors and regulations require banks to have robust governance policies and processes covering among others effective board and senior management oversight and sound control environment. | [5 empty] | i) Applicable guidelines and regulations are drafted. April 2018
|  | RMI | 1.1 Supervisors and regulations require banks to apply sound policies and processes to identify, measure, monitor and control their financial risks on a timely basis and assess their capital adequacy in relation to their risk profile | Follow-up mission from the Regional Workshop on Banking Legislation and Prudential Standards | 5 | 12 | 17 | 1 | i) Applicable guidelines and regulations are drafted. April 2018 | Workshop to review and establish revision plan for banking legislation and prudential standards, to be held in July 2017. Followed up with bilateral missions to each country to follow-up on and progress reform. First follow-up. | February 2018 | Stefanou/ Expert
|  |  | 1.2 Supervisors and regulations require banks to have robust governance policies and processes covering among others effective board and senior management oversight and sound control environment. | [5 empty] | i) Applicable guidelines and regulations are drafted. April 2018
|  | Regional | 1.1 Supervisors and regulations require banks to apply sound policies and processes to identify, measure, monitor and control their financial risks on a timely basis and assess their capital adequacy in relation to their risk profile | Workshop on Banking Legislation and Prudential Standards - sub-regional for Northern Pacific members (FSM, Palau, RMI, Kiribati) | 5 | 12 | 17 | 1 | i) Applicable guidelines and regulations are drafted. April 2018 | Workshop to review and establish revision plan for banking legislation and prudential standards. Workshop will be followed up with bilateral missions to each country to follow-up on and progress reform. | July 2017 | Stefanou/ LEG / Expert
|  |  | 1.2 Supervisors and regulations require banks to have robust governance policies and processes covering among others effective board and senior management oversight and sound control environment. | [5 empty] | i) Applicable guidelines and regulations are drafted. April 2018
|  | Regional | 1.1 Supervisors and regulations require banks to apply sound policies and processes to identify, measure, monitor and control their financial risks on a timely basis and assess their capital adequacy in relation to their risk profile | Workshop on Insurance Legislation and Prudential Standards - sub-regional for Southern Pacific members | 5 | 12 | 17 | 1 | i) Applicable guidelines and regulations are drafted. April 2019 | Workshop to review and establish revision plan for insurance legislation and prudential standards. Workshop will be followed up with bilateral missions to each country to follow-up on and progress reform. | February 2018 | Stefanou/ LEG / Expert
|  |  | 1.2 Supervisors and regulations require banks to have robust governance policies and processes covering among others effective board and senior management oversight and sound control environment. | [5 empty] | i) Applicable guidelines and regulations are drafted. April 2019
Financial Sector Supervision | 2. To implement a risk-based supervision (RBS) system and upgrade other supervisory processes | Cook Islands | 2.4 Strengthened institutional structure and operational and procedures for RBS implementation | RBS framework enhancement program. Second follow-up mission. Develop more in-depth and risk-based on-site examination assessment. | 7 | 16 | 23 | 1 | i) Risk rating model, including impact index, is developed and implemented. October 2018 ii) Risk-based supervisory action planning process developed and implemented. October 2018 | Assisting with documenting on-site examination framework, on-the-job training and technical training in assessment of key bank risk areas. | April 2018 | Stefanou/Expert
|  | FSM | 2.6 Supervisors have sufficient capacity to effectively implement risk-based supervision and other supervisory processes. | Provide training to supervisors on supervision and assessment of banking key risk areas | 0 | 12 | 12 | 1 | 1. A training program is designed and delivered to supervisors | Training is the assessment of credit risk, operational risk, liquidity risk, market risk and investment risk. Training mission to be followed up in 2019 with on-site examination on-the-job training. | April 2018 | Expert
|  | RMI | 2.4 Strengthened institutional structure and operational and procedures for RBS implementation | Provide guidance and training for on-site examination, using an actual on-site examination as a working case. | 0 | 19 | 19 | 1 | i) Use of CAMELS assessment framework embedded in organization. April 2018 | Follow-up TA mission to the on-site examination mission undertaken in February 2017 | July 2017
|  | PNG | 2.4 Strengthened institutional structure and operational and procedures for RBS implementation | RBS framework enhancement program. Diagnostic to assess effectiveness and efficiency of RBS framework and develop TA strategy and plan | 7 | 16 | 23 | 1 | i) RBS Framework Enhancement Strategy and TA Plan developed and initiated. April 2018 | Initial mission to determine current RBS implementation status and identify priority TA | June 2017 | Stefanou/ Expert
|  |  | 2.4 Strengthened institutional structure and operational and procedures for RBS implementation | RBS framework enhancement program. First follow-up mission from diagnostic. Focus to be on a key RBS component: Regulation; Risk Identification and Assessment; Risk Rating; or Supervisory Action Planning | 7 | 16 | 23 | 1 | i) Milestones for follow-up missions to be based on RBS Framework Enhancement Strategy and TA Plan | Continuation of RBS framework enhancement program. Mission scope determined by diagnostic mission. | April 2018 | Stefanou/ Expert
|  | Solomon Islands | 2.4 Strengthened institutional structure and operational and procedures for RBS implementation | RBS framework enhancement program. Diagnostic to assess effectiveness and efficiency of RBS framework and develop TA strategy and plan | 5 | 12 | 17 | 1 | i) RBS Framework Enhancement Strategy and TA Plan developed and initiated. April 2018 | Initial mission to determine current RBS implementation status and identify priority TA | September 2017 | Stefanou/ Expert
|  |  | 2.4 Strengthened institutional structure and operational and procedures for RBS implementation | RBS framework enhancement program. First follow-up mission from diagnostic. Focus to be on a key RBS component: Regulation; Risk Identification and Assessment; Risk Rating; or Supervisory Action Planning | 5 | 12 | 17 | 1 | i) Milestones for follow-up missions to be based on RBS Framework Enhancement Strategy and TA Plan | Continuation of RBS framework enhancement program. Mission scope determined by diagnostic mission. | April 2018 | Stefanou/ Expert
|  | Timor-Leste | 2.6 Supervisors have sufficient capacity to effectively implement risk-based supervision and other supervisory processes. | Provide training to supervisors on supervision and assessment of banking key risk areas | 5 | 0 | 5 | 1 | 1. A training program is designed and delivered to supervisors | Training is the assessment of credit risk, operational risk, liquidity risk, market risk and investment risk. Training mission to be followed up in 2019 with on-site examination on-the-job training. | April 2018 | Expert
|  | Tuvalu | 2.3 Bank risk assessment frameworks strengthened: a) Quality and timeliness of regulatory data enhanced; and b) Flexibility of reporting system improved. | Development of basic prudential reporting framework | 5 | 0 | 5 | 1 | i) Revised Reporting templates are developed. April 2019 | This work will be in addition to the Banking Supervision Program, initiated by PFTAC in FY2017, and now planned to be jointly implemented with the World Bank. | September 2017 | Stefanou
|  | Vanuatu | 2.4 Strengthened institutional structure and operational and procedures for RBS implementation | RBS framework enhancement program. Diagnostic to assess effectiveness and efficiency of RBS framework and develop TA strategy and plan | 7 | 16 | 23 | 1 | i) RBS Framework Enhancement Strategy and TA Plan developed and initiated. October 2017 | Initial mission to determine current RBS implementation status and identify priority TA. Mission on-site undertaken. Finalization of mission work in progress. | May 2017 | Stefanou/ Expert
|  |  | 2.4 Strengthened institutional structure and operational and procedures for RBS implementation | RBS framework enhancement program. First follow-up mission from diagnostic. Focus to be on a key RBS component: Regulation; Risk Identification and Assessment; Risk Rating; or Supervisory Action Planning | 5 | 19 | 24 | 1 | i) Milestones for follow-up missions to be based on RBS Framework Enhancement Strategy and TA Plan | Continuation of RBS framework enhancement program. Mission scope determined by diagnostic mission. | September 2017 | Stefanou/ Expert
|  | Regional | 2.6 Supervisors have sufficient capacity to effectively implement risk-based supervision and other supervisory processes. | AFSPC Annual Meeting. Introduction to: Resolution Frameworks; and Fintech and Supervision | 5 | 12 | 17 | 1 | i) Workshop on Resolution Framework delivered ii) Workshop on Fintech and Supervision delivered |  | August 2017 | Stefanou/ MCMFC
|  |  | 2.6 Supervisors have sufficient capacity to effectively implement risk-based supervision and other supervisory processes. | SEACEN: Provide training to supervisors on supervision and assessment of banking key risk areas | 5 |  | 5 | 1 | i) SEACEN supervision training delivered. | SEACEN is developing a foundation supervision training course. PFTAC will assist SEACEN in delivery of course for PFTAC members. | September 2017 | Stefanou
|  |  |  | Total Days: | 95 | 254 | 349 | 21