## FY2018
Work Plan - May 2017 to April 2018: Public Financial Management (PFM)
TA Area | Objective | Country | Outcome Targeted | Activity | May 2017 - April 2018 |  |  | Number of Missions/ Activities | Milestones | Comments | Planned Date | Experts
(in person-days)
[5 empty] | PFTAC LTX | ST experts | Total
Public Financial Management | 1. Improved laws and effective PFM institutions | Fiji | 1.1 Legal Framework enacted | Revision of Financial Instructions | 0 | 26 | 26 | 2 | Revised Fis developed by PFTAC and adopted by authorities by October 2018 | Assumes parliamentary approval of PFM Act amendment FY18/H1; Involves mission and work from home | April 2018 | Silins
|  | Kiribati | 1.2 MoF capacity can meet enacted PFM responsibilities | PEFA Self-Assessment | 16 | 20 | 36 | 1 | PEFA Self-Assessment completed by August 2017 | With significant country ownership, reviewed by PFTAC | July-Aug 2017 | Neves/Narube
|  | Palau | 1.2 MoF capacity can meet enacted PFM responsibilities | PEFA Self-Assessment | 7 | 18 | 25 | 1 | PEFA Self-Assessment completed Feb 2018 | Developed by authorities and reviewed by PFTAC | 2018-02-01 | Neves/TBA
|  | Solomon Islands | 1.1 Legal Framework enacted | Revision of Financial Instructions | 0 | 36 | 36 | 3 | Revised Fis developed by PFTAC and adopted by authorities by July 2018 | PFTAC to review draft by authorities assumed ready FY18/H1; Involves 2 missions and work from home | January to February 2018 | Mayes
|  | Timor Leste | 1.2 MoF capacity can meet enacted PFM responsibilities | Expenditure Review Seminar | 7 | 0 | 7 | 1 | Participation in the Expenditure Review Seminar | PFTAC participation was requested by the authorities. This seminar will be participated by other development partners | June 2017 | Neves
|  | Tokelau | 1.2 MoF capacity can meet enacted PFM responsibilities | PEFA Self-Assessment and update of PFM Roadmap | 13 | 19 | 32 | 1 | PEFA Self-Assessment completed by September 2017 and PFM Roadmap updated by January 2018 | Developed by authorities and reviewed by PFTAC | September 2017 | Neves/Uluinaceva
|  | Regional | 1.2 MoF capacity can meet enacted PFM responsibilities | Participation in development partners' forum | 28 | 0 | 28 |  | Technical inputs provided as required | Includes participation in development partners forum | between May 2017 to April 2018 | Neves/Marzan
Public Financial Management | 2. Strengthen budget preparation towards more comprehensive, credible, and policy oriented budget. | Fiji | 2.2 More comprehensive and unified annual budget is published | Refinement of budget documents and process | 11 | 0 | 11 | 1 | Fijian budget document continues to expand in terms of content by September 2017 | Work undertaken in-house | June 2017 | Neves
|  | Regional | 2.3 More credible medium-term budget framework is integrated in annual budget process | Workshop on Expenditure Planning & Budget Documentation | 5 | 0 | 5 | 1 | Workshop Delivered as planned. | Collaboratively with Macro advisor, ADB, PIFS, UNESCAP | September 2017 | Neves
Public Financial Management | 3. Improve budget execution and control. | Fiji | 3.1 Budget execution and controls are strengthened | Development of an Internal Audit Charter | 10 | 19 | 29 | 1 | Internal Audit Charter developed by PFTAC and adopted by authorities by December 2017 | One-week on-site and one-week off-site | June 2017 | Morrison/Marzan
|  |  |  | Development of internal control risk framework and audit strategy | 0 | 20 | 20 | 1 | Risk framework and strategic audit plan developed by PFTAC and adopted by authorities by May 2018 |  | October 2017 | Morrison
|  | PNG | 3.1 Budget execution and controls are strengthened | Training Needs Assessment and Internal Auditor Training | 0 | 21 | 21 | 1 | Training completed on PFM Systems Audit of at least large departments | Low PEFA Internal Audit scores due to lack of systems-based audits. | March 2018 | Morrison
|  | Vanuatu | 3.1 Budget execution and controls are strengthened | Strengthening Internal Audit | 0 | 20 | 20 | 2 | 1. Payroll and procurement manual developed by PFTAC by mid November, 2017 2. Auditors trained by PFTAC and using manual by end of November 2017. | Builds on 2016 TA, involves on and off-site work | November 2017 | Prcevich
|  | Regional | 3.1 Budget execution and controls are strengthened | Workshop on strengthening budget execution controls | 7 | 12 | 19 | 1 | Workshop Delivered as planned. | Targets Heads of Treasury and Internal Audit | August 2017 | Marzan/Silins
Public Financial Management | 4. Improve coverage and quality of fiscal reporting | Fiji | 4.1 Chart of Accounts is aligned with International Standards | Phase 2 of improving the Chart of Accounts | 0 | 19 | 19 | 2 | With PFTAC support, all classifications are developed and integrated into CoA and adopted by authorities by October 2017. | Phase 1 completed Feb 2017. On and off-site work by STX. | June/July 2017 | Silins
|  |  | 4.2 Comprehensiveness, frequency, and quality of fiscal reports is enhanced | Implement new government accounting and reporting policies | 12 | 0 | 12 | 1 | 1. Ministry staff trained by April 2018 to implement IPSAS-Cash. 2. MoE staff trained by August 2017 to implement Phase 1 of new procedures. | This will lbe first phase of support | From June 2017 | Marzan
|  | Nauru | 4.2 Comprehensiveness, frequency, and quality of fiscal reports is enhanced | Implement IPSAS Cash Accounting | 0 | 14 | 14 | 1 | 1. Gap analysis, action plan developed by PFTAC and adopted by authorities by March 2018 2. Staff trained on IPSAS-Cash by December 2017. | Part of PFM Roadmap | December 2017 | Mayes
|  | PNG | 4.2 Comprehensiveness, frequency, and quality of fiscal reports is enhanced | Implement IPSAS Cash Accounting | 0 | 19 | 19 | 1 | 1. Gap analysis, action plan developed by PFTAC and adopted by authorities by March 2017 2. Staff trained on IPSAS Cash by November 2017 | Part of PFM Roadmap | November 2017 | Mayes
|  | Samoa | 4.2 Comprehensiveness, frequency, and quality of fiscal reports is enhanced | Improve accounting frameworks on financial assets and liabilities | 7 | 0 | 7 | 1 | 1. PFTAC advice adopted and full IPSAS-cash compliance by authorities by November 2018; 2. Regs on Fin assets/liabilities implemented by July 2018. | Builds on FY17 TA that improved accounting framework; on and off-site work | September 2017 | Marzan
|  | Solomon Islands | 4.2 Comprehensiveness, frequency, and quality of fiscal reports is enhanced | Implement IPSAS Cash Accounting | 0 | 15 | 15 | 2 | 1. MoFT staff trained on IPSAS-Cash implementation by May 2017; 2. 2016 financial report partially meets IPSAS-Cash requirements | Part of PFM Roadmap; on and off-site work | May 2017 | Silins
|  | Tonga | 4.1 Chart of Accounts is aligned with International Standards | Phase 2 of improving the Chart of Accounts | 0 | 12 | 12 | 1 | All required classifications are developed and integrated into new CoA and adopted by authorities by July 2018. | Phase 1 completed March 2017. | July 2017 | Silins
|  |  | 4.2 Comprehensiveness, frequency, and quality of fiscal reports is enhanced | Improve accounting and reporting frameworks | 7 | 0 | 7 | 1 | 1. Staff trained on IPSAS-Cash implementation by July 2017; 2. 16/17 fin statements reviewed by PFTAC and advice partially adopted by authorities by November 2017. | Continuation of 2016 TA for accounting reform | July 2017 | Marzan
|  | Vanuatu | 4.2 Comprehensiveness, frequency, and quality of fiscal reports is enhanced | Scoping mission for capacity development on accounting and reporting | 12 | 19 | 31 | 1 | 1. Gap analysis, action plan developed by PFTAC and adopted by authorities by October 2017; 2. Staff trained on IPSAS application on July 2017. | Part of PFM Roadmap. | July 2017 | Marzan/Uluinaceva
|  |  | 4.2 Comprehensiveness, frequency, and quality of fiscal reports is enhanced | Development of Accounting Manual | 0 | 21 | 21 | 2 | Accounting Manual drafted and adopted by authorities by January 2018. 2. Staff trained on the manual by October 2017. | Involves on and off-site work. | October 2017 | Uluinaceva
Public Financial Management | 5. Improve integration of asset and liability management framework | Samoa | 5.2 Cashflow forecasts for all central government are more accurate and timely | Strengthening Cash Management | 0 | 17 | 17 | 1 | 1. New Cash Management Regs finalized & approved by authorities by June 2018. 2. Staff trained in new Cash Mgmt Regs to prepare cashflow forecast by July 2017. | Builds on initial training provided in 2016. | July 2017 | Silins
|  | Solomon Islands | 5.2 Cashflow forecasts for all central government are more accurate and timely | Strengthening Cash Management | 0 | 13 | 13 | 2 | 1. Cash Mgmt Guidelines finalized, approved and implemented by authorities by January 2018. 2. Staff trained by August 2017 and apply cashflow model. | Builds on initial training provided in 2016; Involves on and off-site work. | May 2017 | Silins
Public Financial Management | 6. Strengthen identification, monitoring, and management of fiscal risks | Fiji | 6.2 Central fiscal oversight and analysis of public corporation risks are strengthened | Identification, monitoring, and management of SOE fiscal risks | 12 | 0 | 12 | 1 | Fiscal risk assessment and reporting framework developed by PFTAC and adopted by authorities by August 2017. | Part of PFM Roadmap. | May 2017 | Marzan
|  | Niue | 6.2 Central fiscal oversight and analysis of public corporation risks are strengthened | Scoping mission to improve fiscal risk analysis | 11 | 0 | 11 | 1 | 1. Deliver seminar on fiscal risks to MoF staff. 2. Key issues and TA needs identified and prioritized. |  | April 2018 | Marzan
|  | Samoa | 6.2 Central fiscal oversight and analysis of public corporation risks are strengthened | Improve fiscal oversight of the financial sector and non-commercial SOEs | 0 | 18 | 18 | 1 | Performance and fiscal risk indicators to monitor SOEs developed by PFTAC and adopted by authorities by October 2017. | Builds on TA on general fiscal oversight of SOEs. To be coordinated with MCM and FSS advisor | June 2017 | Savenaca
|  | Regional | 6.2 Central fiscal oversight and analysis of public corporation risks are strengthened | Identification, monitoring, and management of SOE fiscal risks | 0 | 0 | 0 | 1 | Fiscal risk assessment and reporting framework developed by PFTAC by April 2018. |  | December 2017 | Work by Headquarters from PFTAC budget
|  | Regional | 6.2 Central fiscal oversight and analysis of public corporation risks are strengthened | Workshop of Fiscal Oversight of SOEs | 7 | 12 | 19 | 1 | 1. Workshop delivered. 2. Participant countries identify gaps, next steps and TA needs | Priority for countries with a C or D PEFA score in PEFA category 9 and 10 | February 2018 | Marzan/Colvin
|  |  |  | Total Person Days: | 172 | 390 | 562 | 38
Total Cost (Estimate)