## Sheet2 (hidden)
Anguilla
Antigua & Barbuda
The Bahamas
Barbados
Belize
Bermuda
British Virgin islands
Cayman Islands
Dominica
Grenada
Guyana
Haiti
Jamaica
Montserrat
St. Kitts & Nevis
St. Lucia
St. Vincent & the Grenadines
Suriname
Trinidad & Tobago
Turks & Caicos Islands

## Workplan FY16-REVISED (hidden)
Work Plan (May 2015 to April 2016): Macroeconomics Programming and Analysis
TA Area | Medium-Term Outcome in the Log Frame | Country | Activity: May 2015 - April 2016 | Inputs: May 2015 - April 2016 (in person-weeks) |  |  |  | Updated Inputs at Nov 1, 2016 (person-weeks - changes in red) |  |  |  | % of updated plan delivered at end-Oct | Delivery status | Milestones | Comments
|  |  |  | IMF HQ | CARTAC resident advisors | ST experts | Total | Updated IMF HQ | Updated LTX | Updated STX | Updated Total
Macroeconomic analysis | Outcomes 1-4 | ECCU | Workshop to assist ECCU Macro Policy Units produce an internally consistent set of macro/fiscal projections | 0.1 | 2 | 2 | 4.1 | 1 | 2 | 2 | 5 | 100 | Delivered on May 6-15 May. | All countries producing internally consistent debt projections | Covered cost for WHD Economist to present over two days
|  | Regional | ICD Course on Macroeconomic Diagnostics | 3 | 1 | 0 | 4 | 3 | 1 | 0 | 4 | 0 | Scheduled for March 14-18 in Suriname. | Workshop deliver on global best practice macro surveillance | Topic changed to Macroeconomic Forecasting. Venue and dates confirmed. | Will happen
| 1. Countries are using macroeconomic forecasts as a basis for annual and medium-term budgets (PI 14(ii), FTE 2.1.2) | SVG | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 2 | 0 | 2.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled. Reduced by 1 week. | Macro Policy Unit independently producing forecasts |  | May happen
|  | Dominica | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 100 | Delivered 28 September - 4 October | Macro Policy Unit independently producing forecasts | The one week Fund staff visit is replaced by this mission
|  | Saint Lucia | Review forecasting framework from previous training session | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 2 | 3.1 | 0 | Not yet scheduled. | Scenarios and risks surrounding baseline forecasts are produced | Mission title will change to assist with producing manuals for Macro Policy Unit | Delete
|  | Grenada | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 2 | 0 | 2.1 | 100 | Delivered July 13-17 | Macro Policy Unit independently producing forecasts | Successful mission so unplanned follow up mission added
|  | Trinidad & Tobago | Advise Ministry of Finance on GDP forecasting methodologies and then assist with implementation | 0.1 | 2 | 3 | 5.1 | 0.1 | 2.5 | 3 | 5.6 | 0.32609 | Delivered as part of IMF mission: Sept 15-25, remainder to be delivered in H2 | MoF of T&T producing multi-year projections with detailed scenarios |  | Should happen
|  | St Kitts | Assist MoF with GDP projection frameworks | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Scheduled Feb 22-26 | Fiscal unit internally producing Macro projections |  | Will happen
|  | Anguilla | Follow up mission to assist with medium-term GDP projections | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled. | producing scenarios around baseline projections |  | Complete
|  | Barbados | Training MoF staff in techniques of Macro projections | 0.1 | 2 | 2 | 4.1 | 0.1 | 1 | 0 | 1.1 | 0.45455 | 2 half days delivered on October 15 and October 20. Fiscal rules mission to occur on Nov-4-16 | MoF undertaking GDP projections | Delivered 2 half days of assistance to MoF. Barbados fiscal rules mission allocated to this. STX have been removed | LTX yes, STX MAYBE
|  | Antigua | Assist with real sector analysis and projections (joint with PFM) | 0.1 | 1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | Cancelled: No commitment from authorities | MoF undertaking GDP projections
| 2. Countries annual budgetary process underpinned by a medium-term macro framework (PI 14(i), FTE 2.1.3) | Turks and Caicos | Follow up revenue forecasting workshop to produce final multi-year projections along with beginning training on MTFF | 0.1 | 0 | 1 | 1.1 | 0.1 | 0 | 1 | 1.1 | 0 | Not yet scheduled | SPDD producing multi-year revenue projections | Leaning on cancelling unless hear back from authorities soon | CANCELLED
|  | Bahamas | Introductory visit and assistance with revenue forecasting | 0.1 | 0 | 1 | 1.1 | 0 | 0 | 0 | 0 | 0 | Cancelled: No commitment from authorities | Revenue forecasts underpinned by macro inputs | Multiple emails sent to FS with no response.
|  | Dominica | Follow up mission to assist with medium-term fiscal framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Policy unit operating sound internally consistent macroeconomic framework |  | Should happen
|  | SVG | Assist team in the refinement of MTFF | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Internally consistent MTFF |  | Should happen
|  | Barbados | Training MoF staff in techniques of revenue projections | 0.1 | 0 | 2 | 2.1 | 0.1 | 0 | 2 | 2.1 | 0 | Not yet scheduled | Revenue projections based on sound Macro inputs |  | May happen
|  | Guyana | Developing a medium-term framework |  |  |  | 0 | 0.1 | 3 | 2 | 5.1 | 9.8039 | Week 1 Scheduled for 16-20 November, 2 further weeks planned but unscheduled | Improved medium-term framework | This unplanned mission was born out of the election | LTX yes, STX MAYBE
|  | Regional | Revenue forecasting and tax policy modelling workshop |  |  |  |  | 3 | 1 | 0 | 4 | 0 | Aiming for late April | Improved medium-term framework | FAD workshop, previously not programmed | Moved to next FY
| 3. Countries adequately reporting on macroeconomic risks and policy (PI 5) | Regional | Workshop - medium term economic and fiscal outlook statements (jointly with CARTAC PFM) | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 100 | Delivered in July | Workshop delivered. Action Plans to implement workshop learnings produced.
|  | Regional | Joint workshop with FS (Shelton) on Macro-Financial linkages | 0.1 | 1 | 1 | 2.1 | [5 empty] | Unscheduled | Modelling capacity built for central bankers to better monitor macro risks to the economy | To discuss with David, Budget dependent
|  | Dominica | Assist with economic reporting | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Further reporting on macroeconomic events |  | Should happen
|  | Saint Lucia | Improving research capacity | 0.1 | 1 | 2 | 3.1 | 0.1 | 1 | 2 | 3.1 | 0 | Scheduled Jan 11-15 | Policy and research papers produced | STX will be Winston Moore | May happen
| 4. Improved macroeconomic and fiscal coordination | Barbados | Provide advice on setting up a macro policy unit | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Scheduled November 4-16 | Policy unit set up | Rolled into FAD fiscal rules mission | Complete
|  | Regional | Workshop for Financial Secretaries (jointly with CARTAC PFM) | 0.1 | 1 | 0 | 1.1 | [5 empty] | Cancelled due to shifting prioties, another regional workshop added. | Workshop delivered. Action Plans to implement workshop learnings produced.
|  |  |  | 5.1 | 23 | 14 | 42.1
|  |  | Original Plan: | 5.1 | 23 | 14 | 42.1
|  |  | Updated Plan at Nov 1: |  |  |  |  | 8.7 | 23.5 | 14 | 46.2
Delivered at Nov 1:
Percentage of Original Plan:
Percentage of Adjusted Plan:

## Revenue
FY18 Work Plan - May 2017 to April 2018: Revenue Administration
TA Area | Objective | Country | Outcome Targeted | Activity | May 2017 - April 2018 |  |  | Number of Missions/ Activities | Milestones | Comments | Planned Date | Experts
(in person-days)
[5 empty] | PFTAC resident advisors | ST experts | Total
Revenue Administration | 1. Strengthened revenue administration management and governance arrangements | Fiji | 1.5 Corporate priorities and compliance better managed through risk management | Strengthen compliance risk management | 0 | 18 | 18 | 1 | Risk based compliance improvement strategy (customs and tax integrated) institutionalized and supported by a governance framework by 12/31/2017. | Fiji has introduced a risk based compliance strategy which needs to be further embedded and integrated with customs. | January 2018 | Aslett
|  | FSM | 1.1 Reform strategy and implementation governance framework adopted and institutionalized | Strategy and governance arrangements in place to support reform initiatives. | 5 | 0 | 5 | 1 | Reform strategy and governance framework designed by and agreed to by 12/31/2018. | Review overall reform progress and support the development of a more structured approach to reforms. | May 2017 | Shrosbree
|  | Kiribati | 1.2 Organizational arrangements enable more effective delivery of strategy and reforms | Strengthen organizational design. | 0 | 10 | 10 | 1 | An organizational structure in place and suitably staffed by 12/31/2017. | Kiribati has introduced a new structure with more TA needed to facilitate implementation. | July 2017 | Scott
|  |  | 1.5 Corporate priorities and compliance better managed through risk management | Develop a risk based compliance improvement strategy | 0 | 8 | 8 |  | Risk based compliance improvement strategy adopted by 12/31/2017. | Kiribati has introduced a new structure with the next phase of modernization linked to introducing a compliance improvement strategy.
|  | Niue | 1.2 Organizational arrangements enable more effective delivery of strategy and reforms | Strengthen organization design. BTB with mission Taxpayer Service Mission 2.2 | 5 | 0 | 5 | 1 | An organizational structure in place and suitably staffed by 6/30/2018. | Niue has accepted PFTAC recommendations to introduce a new structure and will require additional TA moving forward. | August 2017 | Shrosbree
|  | Palau | 1.1 Reform strategy and implementation governance framework adopted and institutionalized | Strategy and governance arrangements in place to support reform initiatives. Review overall reforms and governance framework. | 1 | 0 | 1 | 1 | Reform strategy and governance framework designed and agreed to by 06/30/2018. | Review overall reform progress and support the development of a more structured approach to reforms. Overlaps STX mission for Organization Reform below | May 2017 | Shrosbree
|  |  | 1.2 Organizational arrangements enable more effective delivery of strategy and reforms | Strengthen organizational design. BTB with Taxpayer Services Mission under 2.2 | 0 | 8 | 8 |  | Organizational structure in place and suitably staffed by 12/31/2018. | Palau has accepted PFTAC recommendations and implemented a function based structure |  | McNeill
|  | PNG | 1.1 Reform strategy and implementation governance framework adopted and institutionalized | Strategy and governance arrangements in place to support reform initiatives | 0 | 15 | 15 | 1 | Strategic and modernization plan in place and supported by a governance structure by 12/31/2017 | PNG has requested PFTAC assistance in renewing the strategic plan. | July 2017 | McNeill
|  | Regional | 1.5 OCO Annual Conference | Developing an alliance with the OCO to improve revenue administration risk management. | 5 |  | 5 | 1 | Attend OCO Conference in Guam and deliver a presentation on integrated risk management. | To support DRM, PFTAC and the OCO have entered into strategic partnership to improve risk management between tax and customs departments. | May 2017 | Shrosbree
|  |  | 1.1 - 1.7 Senior Management Team Workshop on modern revenue administration (to follow PITAA Heads Meeting) | Management of tax administration strategies and operations improve over time. | 3 | 3 | 6 | 1 | Workshop will reemphasize the important of a reform strategy, governance, support functions and risk management in modern tax administration. | To support management development PFTAC will reemphasize the importance of reform, governance and risk management in modern tax administration. | September 2017 | Shrosbree
|  | RMI | 1.1 Reform strategy and implementation governance framework adopted and institutionalized | Strategy and governance arrangements in place to support reform initiatives. | 3 | 0 | 3 | 1 | A commitment by Government to kick start reforms by 30 June, 2017. | Review overall reform progress and support the development of a more structured approach to reforms | May 2017 | Shrosbree
|  | Samoa | 1.5 Corporate priorities and compliance better managed through risk management | Further strengthen compliance risk management. | 0 | 18 | 18 | 1 | Compliance risks identified and addressed through an evidenced based implemented compliance improvement strategy by 12/31/2017. | Samoa introduced a compliance improvement strategy but implementation support is required | October 2017 | Aslett
|  |  | 1.5 Corporate priorities and compliance better managed through risk management | Further strengthen compliance risk management. | 12 |  | 12 | 1 | Compliance risks identified and addressed through an evidenced based implemented compliance improvement strategy by 12/31/2017. | Samoa introduced an Industry Partnership initiative - additional implementation assistance required. | October 2017 | Shrosbree
|  | Tuvalu | 1.2 Organizational arrangements enable more effective delivery of strategy and reforms | Strengthen organizational design. | 12 | 0 | 12 | 1 | Organizational structure in place and suitably staffed by 6/30/2018. | Tuvalu has accepted PFTAC recommendations to improve its current structure and adopt a more functional approach | August 2017 | Shrosbree
|  | Vanuatu | 1.1 Reform strategy and implementation governance framework adopted and institutionalized | Review overall reforms and governance framework. | 5 | 0 | 5 | 1 | Successful implementation of a reform strategy and governance framework to manage reforms. | Review overall reform progress and reform governance framework. | November 2017 | Shrosbree
|  |  | 1.2 Organizational arrangements enable more effective delivery of strategy and reforms | Strengthen organizational design | 0 | 18 | 18 | 1 | Organizational structure in place and suitably staffed by 12/31/2017. | Vanuatu recently introduced a new function based structure under PFTAC guidance – additional TA is to refine the model | July 2017 | McNeill
|  |  | 1.5 Corporate priorities and compliance better managed through risk management | Further strengthen compliance risk management. | 12 | 0 | 12 | 1 | Risk based compliance improvement strategy institutionalized and supported by a governance framework in line with TADAT dimensions by 12/31/2017. | Vanuatu introduced a compliance improvement strategy and has made some progress – TA will help institutionalize the approach. | June 2017 | Shrosbree
Revenue Administration | 2. Strengthened core functions evidenced by an accurate taxpayer base, taxpayer services supporting voluntary compliance, improvements in filing, payment and audit activities | Fiji | 2.2 Taxpayer Services initiatives to support voluntary compliance strengthened | Strengthen the taxpayer services function. | 0 | 12 | 12 | 1 | Taxpayer services strategy in place and operating at improved efficiency rates in line with TADAT dimensions by 6/30/2018. | Fiji’s taxpayer services initiatives are to be consolidated under a new structure. TA will be provided to assist in the process. | November 2017 | Scott
|  |  | 2.3 Larger proportion of taxpayers meet their filing obligations as required by law | Improve on-time filing ratios over time. | 0 | 18 | 18 | 1 | On-time filing operating at improved efficiency levels in line with TADAT dimensions by 12/31/2018.. | On-time filing has improved but opportunity exists to further enhance performance. Additional TA will assist to further improve business processes. | February 2018 | Lawrence
|  |  | 2.5 Audit and other verification programs more effectively ensure completeness and accuracy of reporting | Strengthen audit capability and programs to ensure completeness and accuracy of reporting. | 0 | 18 | 18 | 1 | The audit function operating at improved efficiency levels in line with TADAT dimensions by 12/31/2019. | Fiji has commenced the restructuring of audit and require additional TA moving forward. | March 2018 | Teed
|  | FSM | 2.3 Larger proportion of taxpayers meet their filing obligations as required by law | Improve on-time filing ratios over time. | 0 | 9 | 9 | 1 | On-time filing operating at improved efficiency levels in line with TADAT dimensions by 12/31/2019. | An environmental scan shows potential to improve on-time filing. | August 2017 | Bell
|  |  | 2.4 Larger proportion of taxpayers meet their payment obligations as required by the law | On-time payment compliance and management of arrears improves over time. | 0 | 9 | 9 |  | On-time payment operating at improved efficiency levels in line with TADAT dimensions by 12/31/2019. | An environmental scan shows potential to improve on-time payment of taxes.
|  |  | 2.2 Taxpayer Services initiatives to support voluntary compliance strengthened | Strengthen the taxpayer services function | 0 | 14 | 14 |  | Taxpayer services strategy in place and operating at improved efficiency rates in line with TADAT dimensions by 30/06/2018. | A new taxpayer services function has been established but needs to be developed.
|  | Kiribati | 2.1 Integrity of the registered taxpayer base strengthened | Strengthen the integrity of the registered taxpayer base | 0 | 9 | 9 | 1 | An improved and more reliable and accurate taxpayer base aligned to TADAT dimensions by 12/31/2018. | Evidence suggests that TA is required in this area. | September 2017 | Scott
|  |  | 2.2 Taxpayer Services initiatives to support voluntary compliance strengthened | Strengthen the taxpayer services function. | 0 | 7 | 7 |  | Taxpayer services strategy in place and operating at improved efficiency levels and based on TADAT dimensions by 12/31/2018. | A new taxpayer services function has been created under a new structure. Additional TA will be provided to guide implementation
|  |  | 2.5 Audit and other verification programs more effectively ensure completeness and accuracy of reporting | Audit and other initiatives effectively detect inaccurate reporting. | 0 | 10 | 10 | 1 | The audit function operating at improved efficiency levels based on TADAT foundations by 12/31/2018. | Kiribati has requested additional TA to build audit capability. | October 2017 | Leano
|  | Niue | 2.2 Taxpayer Services initiatives to support voluntary compliance strengthened | Strengthen the taxpayer services function. BTB with Organization Mission 1.2 | 5 | 0 | 5 | 0 | Taxpayer services strategy in place by 6/30/2018 and aligned to TADAT dimensions. | A new structure to be implemented which will include setting up a taxpayer services component.. | August 2017 | Shrosbree
|  | Palau | 2.2 Taxpayer Services initiatives to support voluntary compliance strengthened | Strengthen the taxpayer services function. BTB with Organization Mission 1.2 | 0 | 15 | 15 | 0 | Taxpayer services strategy designed by 07/31/2017 and implemented by 12/31/2017 and aligned to TADAT dimensions. | Palau has accepted PFTAC recommendations to introduce a new function based structure and will need additional TA to build an effective taxpayer services program. | May 2017 | McNeill
|  | PNG | 2.1 Integrity of the registered taxpayer base strengthened | Integrity of the registered taxpayer base strengthened. | 0 | 15 | 15 | 1 | A reliable and accurate taxpayer base aligned to TADAT dimensions by 07/31/2018. | The current data base is corrupt - the authorities have requested PFTAC advise to rectify. | June 2017 | Lawrence
|  |  | 2.3 Larger proportion of taxpayers meet their filing obligations as required by law | Improve on-time filing rates over time. |  |  |  |  | On-time filing operations based on TADAT dimensions with improvements by 6/30/2018. | The authorities have requested PFTAC TA to assist in improving on-time filing ratios.
|  |  | 2.4 Larger proportion of taxpayers meet their payment obligations as required by the law | On-time payment compliance and management of arrears improves over time |  |  |  |  | On-time payment operations based on TADAT dimensions with improvements by 6/30/2018. | The authorities have requested PFTAC assistance to improve poor on-time payment levels.
|  | Regional | 1&2 PITAA Heads Meeting - Management and core tax functions | Reviewing regional progress during 2016/17 and planning ahead. | 5 |  | 5 | 1 | Annual PITAA Heads Meeting (Samoa) | PFTAC supporting the development of PITAA | September 2017 | Shrosbree
|  |  | 2.5 Audit and other verification programs more effectively ensure completeness and accuracy of reporting | VAT Fraud Workshop with PITAA | 0 | 8 | 8 | 1 | PICs have little awareness of VAT fraud schemes and need to understand and build capability to address tax leakage in this area. | To support VAT risk management PFTAC will facilitate a VAT fraud workshop to highlight area of risk. | October 2017 | STX
|  |  | 2.5 Audit and other verification programs more effectively ensure completeness and accuracy of reporting | Management training for senior auditors and managers. | 5 | 0 | 5 | 1 | PICs need to develop management skills to improve the management of the audit functions. | Upon the request of PICs PFTAC will facilitate a workshop geared towards improving audit management capability. | December 2017 | Shrosbree
|  |  | 2.5 Audit and other verification programs more effectively ensure completeness and accuracy of reporting | Senior auditor training in the interpretation and analysis of financial statements - | 0 | 12 | 12 | 1 | PICs need to develop audit skills to interpret and analyze corporate financial statements to detect compliance anomalies. | The larger PICs have requested PFTAC training to develop skills that provide a better understanding of corporate financial statements and tax implications. | July 2017 | Teed
|  | RMI | 2.1 Integrity of the registered taxpayer base strengthened | Strengthen the integrity of the registered taxpayer base. | 0 | 9 | 9 | 1 | A reliable and accurate taxpayer base aligned to TADAT dimensions by 12/31/2017. | The current data base is corrupt - the authorities have requested PFTAC advise to rectify. | Octber 2017 | Lawrence
|  |  | 2.2 Taxpayer Services initiatives to support voluntary compliance strengthened | Strengthen the taxpayer services function. | 0 | 7 | 7 |  | Taxpayer services strategy in place by 12/31/2017 and aligned to TADAT dimensions. | Additional TA required in setting up a sustainable taxpayer services program.
|  |  | 2.3 Larger proportion of taxpayers meet their filing obligations as required by law | Improve on-time filing ratios over time. | 0 | 9 | 9 | 1 | On-time filing improvements based on TADAT dimensions in place and reflected in improvements achieved by 12/31/2017. | An environmental scan shows potential to improve on-time filing. | January 2018 | Lawrence
|  |  | 2.4 Larger proportion of taxpayers meet their payment obligations as required by the law | On-time payment compliance and management of arrears improves over time. | 0 | 7 | 7 |  | On-time payment improvements demonstrated and in line with TADAT dimensions by 12/31/2017. | An environmental scan shows potential to improve on-time payment of taxes
|  |  | 2.5 Audit and other verification programs more effectively ensure completeness and accuracy of reporting | Strengthen audit capability and programs to ensure completeness and accuracy of reporting. | 0 | 15 | 15 | 1 | The audit function operating at improved efficiency levels in line with TADAT dimensions by 12/31/2018. | RMI has a low audit skills base and requested TA to build capability. | July 2017 | Leano
|  | Samoa | 2.3 Larger proportion of taxpayers meet their filing obligations as required by law | Improve on-time filing ratios over time | 0 | 15 | 15 | 1 | On-time filing operating at improved efficiency levels in line with TADAT dimensions and showing improvements by 6/30/2018. | The authorities have requested TA to improve on-time filing rates. | November 2017 | Lawrence
|  |  | 2.4 Larger proportion of taxpayers meet their payment obligations as required by the law | On-time payment compliance and management of arrears improves over time. | 0 | 15 | 15 |  | On-time payment improvements demonstrated and in line with TADAT dimensions by 12/31/2017. | Opportunity exists to further strengthen on-time payment of taxes.
|  |  | 2.5 Audit and other verification programs more effectively ensure completeness and accuracy of reporting | Building audit capability and programs to ensure completeness and accuracy of reporting | 0 | 18 | 18 | 1 | The audit function operating at improved efficiency levels in line with TADAT dimensions by 12/31/2018. | Building audit capability is a long term effort which will require TA moving forward. | October 2017 | Teed
|  | Tonga | 2.3 Larger proportion of taxpayers meet their filing obligations as required by law | Improve on-time filing rates over time. | 0 | 7 | 7 | 1 | On-time filing operating at improved efficiency levels in line with TADAT dimensions and showing improvements by 6/30/2018. | The authorities have requested TA to improve on-time filing rates. | March 2018 | Lawrence
|  |  | 2.4 Larger proportion of taxpayers meet their payment obligations as required by the law | Building audit capability and programs to ensure completeness and accuracy of reporting | 0 | 9 | 9 | 1 | The audit function operating at improved efficiency levels in line with TADAT dimensions by 12/31/2018. | Opportunity exists to further strengthen on-time payment of taxes. | July 2017 | Teed
|  | Vanuatu | 2.3 Larger proportion of taxpayers meet their filing obligations as required by law | Improve on-time filing rates over time. | 0 | 15 | 15 | 1 | On-time filing operating at improved efficiency levels in line with TADAT dimensions and showing improvements by 12/31/2017. | Progress has been made to improve on-time filing with more work required to improve internal business processes. | August 2017 | McNeill
|  |  | 2.4 Larger proportion of taxpayers meet their payment obligations as required by the law | On-time payment compliance and management of arrears improves over time. |  | 15 | 15 |  | On-time payment improvements demonstrated and in line with TADAT dimensions by 12/31/2017. | Vanuatu requested additional TA after an environmental scan showed opportunity to improve on-time payment ratios.
|  |  |  | Total Days: | 78 | 395 | 473 | 34