## Macro
FY18 Work Plan - May 2017 to April 2018: Macroeconomic Management
TA Area | Objective | Country | Macroeconomic Programming & Analysis LogFrame Outcome Targeted | Activity | May 2017 - April 2018 |  |  | Number of Missions/ Activities | Milestones | Comments | Planned Date | Experts
(in person-days)
[5 empty] | PFTAC resident advisors | ST experts | Total
Macroeconomic Management | 1. Improved macroeconomic policy advice to government and central bank management | Samoa | 1.1 Improved quality and frequency of macroeconomic surveillance and policy/research available for policymaking | Develop GDP forecasting methodology. | - | 21 | 21 | 1 | 1) A GDP forecasting framework is set up (Dec. 17). (2) Three-year forecasts of real GDP by industries and the GDP deflator are produced by the Central Bank of Samoa and the Ministry of Finance (Dec. 17). (3) A forecasting committee is established and forecasts are shared with other institutions, e.g. Ministry for Revenue (Jun. 18). (4) The forecasting committee produces and publishes official forecasts (Jun. 19). |  | TBD | ??????
|  | Tuvalu |  | Develop GDP forecasting methodology. | 5 | 0 | 5 | 1 | 1) GDP forecasting methodology is developed (Sept. 17). (2) Three-year forecasts of real GDP and the GDP deflator are produced (Jun. 18). |  | July 2017 | Claus
|  | Regional |  | Workshop on compiling and forecasting GDP. | 5 | 9 | 14 | 1 | 1) An inter-disciplinary workshop is facilitated (Oct. 17). (2) Participants identify priority areas for improving GDP compilation and forecasting (Oct. 17). | The workshop will be organized in collaboration with PFTAC’s Real Sector Statistics Advisor. | October 2-6, 2017 | Claus/?????
|  | Regional |  | Workshop on forecasting fishing revenues. | 5 | 14 | 19 | 1 | 1) An inter-disciplinary workshop is facilitated (Feb. 18). (2) Participants identify priority areas for improving fishing revenue forecasting and management (Feb. 18). (3) Medium-term fishing revenue projections are produced jointly by ministries of finance and marine authorities in 2 out of 9 countries (Sept. 18). | The workshop will be organized in collaboration with PFTAC’s PFM Advisor. | February 12-17 2018 | Claus/?????
|  | Regional |  | Workshop on incorporating demographic changes into budget processes. | 5 |  | 5 | 1 | 1) An inter-disciplinary workshop is facilitated (Nov. 17). (2) Economic and fiscal projections include demographic changes in 2 out of 8 countries (Nov. 18). | The workshop will be organized in collaboration with PFTAC’s PFM Advisor and UNESCAP. | November 27-December 1, 2017 | Claus
|  | Regional |  | Support and advise on econometric estimations, including of a measure of the output gap, and empirical analysis. | 5 | 5 | 10 | 1 | 1) Analytical advice & support is provided as requested (Apr. 18). (2) Research papers are peer reviewed (Apr. 18). (3) At least two working papers are published by Pacific central banks and/or ministries of finance (Apr. 18). 4) Options to estimate potential output using multivariate filter methodology developed by the IMF Research Department are investigated (Apr. 18). | Technical assistance will be provided offsite. | On-going | Claus/?????
Macroeconomic Management | 1. Improved macroeconomic policy advice to government and central bank management | Cook Islands | 1.2 Sound medium-term macroeconomic framework | Support the use of the Cook Islands macroeconomic and fiscal framework. | 5 | 0 | 5 | 1 | 1) Assistance is provided as required to ensure sustained use of the Cook Islands macroeconomic and fiscal framework in budget preparations (Apr. 18). |  | October 2017
|  | Fiji |  | Develop the Fiji financial programming framework to undertake debt sustainability and external vulnerability assessments. | 10 | 0 | 10 | 1 | 1) Macro-financial stability indicators are included in the Fiji financial programming (FP) framework (Sept. 17). (2) Methodology is developed to map data between calendar and fiscal years (Dec. 17). (3) An inter-agency workshop on practical applications of the Fiji financial programming framework is facilitated (Dec. 17). (4) The fiscal sector in the macroeconomic framework adopts official GFS methodology (Nov. 18). (5) Assistance is provided as required to ensure sustained use of the Fiji FP framework (Apr. 18). |  | On-going | Claus
|  | PNG |  | Continue developing a macroeconomic and fiscal framework. | 15 | 0 | 15 | 2 | 1) The PNG macroeconomic and fiscal framework is developed further (Dec. 17). (2) The projection horizon is extended to the medium term (Dec. 17). (3) The PNG macroeconomic and fiscal framework is developed to undertake debt sustainability assessments (Mar. 18). (4) The framework is used to support monitoring and projection activities by the Bank of Papua New Guinea and the Department of Treasury (Jun. 18). (5) Assistance is provided as required to ensure sustained use of the PNG macroeconomic and fiscal framework (Apr. 18). |  | May 20-June 4, 2017, October 2017 | Claus
|  | RMI |  | Support the use of the Marshall Islands Fiscal Model (MI-FM) in budget preparations and policy analysis. | 15 | 0 | 15 | 2 | 1) Development of the MI-FM is completed (Dec. 17). (2) The MI-FM is used for policy analysis including to develop a medium-term fiscal framework (Dec. 17). (3) Quarterly Government Finance Statistics (GFS) and outturns compared to forecasts are reported on (Dec. 17). (4) Staff resources to update and use the MI-FM are increased (Mar. 18). (5) Staff update and use the MI-FM in budget prep (Aug. 18). (6) Assistance is provided as need to ensure sustained use of the MI-FM (Apr. 18). |  | May 1-5, 2017, November 2017 | Claus
|  | Samoa |  | Develop the Samoa Economic and Revenue Forecasting (SERF) Model to undertake debt sustainability analysis and monitor cash and foreign reserves. | 5 | 0 | 5 | 1 | 1) The projection horizon of the SERF Model is extended to the medium term (Sept. 17). (2) The SERF model is developed to undertake sustainability analysis of policy scenarios (Apr. 18). (3) Assistance is provided as required to ensure sustained use of the SERF Model (Apr. 18). |  | July 2017 | Claus
|  | Solomon Islands |  | Develop the Solomon Islands financial programming frameworks to undertake debt sustainability and external vulnerability assessments. | 10 | 0 | 10 | 2 | 1) The projection horizons of the Central Bank of Solomon Islands' and the Ministry of Finance and Treasury's financial programming frameworks are extended to the medium term (Dec. 17). (2) The frameworks are developed to undertake sustainability analysis of policy scenarios (Jun. 18). (3) Assistance is provided as required to ensure sustained use of the Solomon Islands' financial programming frameworks (Apr. 18). |  | September 2017, February 2018 | Claus
|  | Tonga |  | Support the use of the Tonga macroeconomic programming framework. | 5 | 0 | 5 | 1 | 1) Assistance is provided as required to ensure sustained use of the Tonga projection model (Apr. 18). |  | March 2018 | Claus
|  | Vanuatu |  | Support the use of the national framework for revenue forecasting in budget preparations and the Model of the Vanuatu Economy (MOVE) to produce economic projections. | 5 | 0 | 5 | 1 | 1) Empirical tools are enhanced further, e.g. to incorporate cash reserve monitoring and better management of debt servicing payments (Apr. 18). (2) Further training is delivered on practical applications of the national framework for revenue forecasting and the MOVE (Jan. 18). (3) Staff at the Ministry of Finance and Economic Management and the Reserve Bank of Vanuatu update and use the tools developed (Apr. 18). (4) A paper documenting the MOVE is published (Apr. 18). (5) Assistance is provided as required to ensure sustained use of the national framework for revenue forecasting and the MOVE (Apr. 18). |  | August 2017 | Claus
|  |  |  | Quantify the price and inflation effects of import duty reductions. | 5 | 0 | 5 | 1 | 1) Methodology is developed to quantify the price and inflation effects of import duty reductions (Aug. 17).(2) Expected price reductions are announced prior to import duty reductions (Jun. 18). | The element of the mission is part of the TA PFTAC has been providing to support the implementation of income tax in Vanuatu. | January 2017 | Claus
|  | Regional |  | Workshop on macroeconomic policy analysis. | 5 | 14 | 19 | 1 | 1) An inter-agency workshop is facilitated (Apr. 18). (2) Collaboration between central banks and ministries of finance is strengthened in the development of policy tools (Apr. 19). |  | April 2018 | Claus/?????
Macroeconomic Management | 1. Improved macroeconomic policy advice to government and central bank management | Samoa | 1.3 Strong institutional structures for macroeconomic policy making | Facilitate a cross institution (Ministry of Finance, Ministry for Revenue, Central Bank of Samoa, Samoa Bureau of Statistics) workshop on forecasting and sharing data. | 5 | 0 | 5 | 1 | 1) An inter-agency workshop is facilitated (Apr. 18).(2) An action plan for improving forecasting and data sharing is agreed by the Central Bank of Samoa, the Ministry of Finance, the Ministry for Revenue, and the Samoa Bureau of Statistics and implemented (Jun. 18). | The establishment of a forecasting committee will be discussed at the workshop. | April 2018 | Claus
|  |  | Total Days: |  | 110 | 63 | 173 | 20

## tims038b_8407354
Benf. Cntry | Site Cntry | Mission id | Site Code | Description | Mission Status | Name | TA Number | Emplid | Deptid | Start Dt | End Dt | Days Total | Days in period | Adj Days | FS | Project Id | Activity id | Donor Ref.# | TRE TC Assign
Cook Islands | COK | 507794 | 531 | support the use of the Cook Islands macroeconomic framework | P | Claus Iris |  | 727818 | APD | 2017-05-21 | 2017-05-30 | 10 | 10 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Fiji | FJI | 508159 | 531 | Develop the FP framework to undertake debt sustainability and external vulnerability assessments | P | Claus Iris |  | 727818 | APD | 2017-06-01 | 2017-06-10 | 10 | 10 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Marshall Islands | MHL | 508890 | 531 | Support the use of the MI-FM in budget preparations | A | Claus Iris | 311606 | 727818 | APD | 2017-05-01 | 2017-05-07 | 7 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
PFTAC-Pacific Finan'l Tech Ass | FJI | 18APZ5400 | 530 | Workshop on compiling and forecasting GDP | P | Claus Iris |  | 727818 | APD | 2017-10-02 | 2017-10-05 | 4 | 4 | 0 | PT | MAC_PFT_2017_05 | SEMINAR_STUDYTR
PFTAC-Pacific Finan'l Tech Ass | FJI | 18APZ5500 | 530 | Workshop on forecasting fishing revenues | P | Claus Iris |  | 727818 | APD | 2017-12-04 | 2017-12-08 | 5 | 5 | 0 | PT | MAC_PFT_2017_05 | SEMINAR_STUDYTR
PFTAC-Pacific Finan'l Tech Ass | FJI | 18APZ5600 | 530 | Workshop on incorporating demographic changes into budget process | P | Claus Iris |  | 727818 | APD | 2018-01-08 | 2018-01-12 | 5 | 5 | 0 | PT | MAC_PFT_2017_05 | SEMINAR_STUDYTR
PFTAC-Pacific Finan'l Tech Ass | FJI | 18APZ5700 | 530 | Workshop on macroeconomic policy analysis | P | Claus Iris |  | 727818 | APD | 2018-03-05 | 2018-03-09 | 5 | 5 | 0 | PT | MAC_PFT_2017_05 | SEMINAR_STUDYTR
Papua New Guinea | PNG | 508525 | 531 | Continue developing a macroeconomic and fiscal framework | A | Claus Iris | 312943 | 727818 | APD | 2017-05-19 | 2017-06-04 | 17 | 17 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Samoa | WSM | 511081 | 531 | Facilitate a cross institution workshop on forecasting and sharing data (MOF MOR CBS BOS) | P | Claus Iris |  | 727818 | APD | 2017-09-17 | 2017-09-23 | 7 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Samoa | WSM | 18APY4000 | 510 | Develop GDP forecasting methodology | P | EXPERT |  |  | APD | 2017-10-01 | 2017-10-21 | 21 | 21 | 0 | PT | MAC_PFT_2017_05 | STX_DELIVERY
Solomon Islands | SLB | 509620 | 531 | Develop the FP framework to undertake sustainability and external vulnerability assessments | P | Claus Iris |  | 727818 | APD | 2017-08-01 | 2017-08-07 | 7 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Solomon Islands | SLB | 496106 | 531 | Facilitate a cross institution workshop (MOF CBSI NSO) on forecasting and sharing data | P | Claus Iris |  | 727818 | APD | 2017-11-01 | 2017-11-07 | 7 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Tonga | TON | 507429 | 531 | Continue developing the Ministry of Revenue & Customs' revenue forecasting tool | P | Claus Iris |  | 727818 | APD | 2017-05-01 | 2017-05-07 | 7 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Vanuatu | VUT | 509986 | 531 | Incorporate cash reserve monitoring into the MOVE | P | Claus Iris |  | 727818 | APD | 2017-08-13 | 2017-08-19 | 7 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Vanuatu | VUT | 510351 | 531 | Support the use of the national framework for revenue forecasting in budget preparations | P | Claus Iris |  | 727818 | APD | 2017-08-21 | 2017-08-27 | 7 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Vanuatu | VUT | 510351 | 531 | Quantify the price and inflation effects of import duty reductions | P | Claus Iris |  | 727818 | APD | 2017-09-01 | 2017-09-07 | 7 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Corrected and updated
Cook Islands | COK | 507794 | 531 | Support the use of the Cook Islands macroeconomic and fiscal framework. | P | Claus Iris |  | 727818 | APD | 2017-10-09 | 2017-10-13 | 5 | 10 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Fiji | FJI | 508159 | 531 | Develop the Fiji financial programming framework to undertake debt sustainability and external vulnerability assessments. | P | Claus Iris |  | 727818 | APD | 2018-03-26 | 2018-04-06 | 12 | 10 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Marshall Islands | MHL | 508890 | 531 | Support the use of the Marshall Islands Fiscal Model (MI-FM) in budget preparations and policy analysis. | A | Claus Iris | 311606 | 727818 | APD | 2017-05-01 | 2017-05-05 | 5 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Marshall Islands | MHL |  |  | Support the use of the Marshall Islands Fiscal Model (MI-FM) in budget preparations and policy analysis. | [5 empty] | 2017-11-06 | 2017-11-17 | 12
PFTAC-Pacific Finan'l Tech Ass | FJI | 18APZ5400 | 530 | Workshop on compiling and forecasting GDP. | P | Claus Iris |  | 727818 | APD | 2017-10-02 | 2017-10-06 | 5 | 4 | 0 | PT | MAC_PFT_2017_05 | SEMINAR_STUDYTR
PFTAC-Pacific Finan'l Tech Ass |  |  |  | Workshop on compiling and forecasting GDP. |  | EXPERT |  |  |  | 2017-10-02 | 2017-10-10 | 9
PFTAC-Pacific Finan'l Tech Ass | FJI | 18APZ5500 | 530 | Workshop on forecasting fishing revenues. | P | Claus Iris |  | 727818 | APD | 2018-02-12 | 2018-02-16 | 5 | 5 | 0 | PT | MAC_PFT_2017_05 | SEMINAR_STUDYTR
PFTAC-Pacific Finan'l Tech Ass |  |  |  | Workshop on forecasting fishing revenues. |  | EXPERT |  |  |  | 2018-02-12 | 2018-02-25 | 14
PFTAC-Pacific Finan'l Tech Ass | FJI | 18APZ5600 | 530 | Workshop on incorporating demographic changes into budget processes. | P | Claus Iris |  | 727818 | APD | 2017-11-27 | 2017-12-01 | 5 | 5 | 0 | PT | MAC_PFT_2017_05 | SEMINAR_STUDYTR
PFTAC-Pacific Finan'l Tech Ass | FJI | 18APZ5700 | 530 | Workshop on macroeconomic policy analysis. | P | Claus Iris |  | 727818 | APD | 2018-04-09 | 2018-04-13 | 5 | 5 | 0 | PT | MAC_PFT_2017_05 | SEMINAR_STUDYTR
PFTAC-Pacific Finan'l Tech Ass |  |  |  | Workshop on macroeconomic policy analysis. |  | EXPERT |  |  |  | 2018-04-09 | 2018-04-22 | 14
Papua New Guinea | PNG | 508525 | 531 | Continue developing a macroeconomic and fiscal framework. | A | Claus Iris | 312943 | 727818 | APD | 2017-05-22 | 2017-06-02 | 12 | 17 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Papua New Guinea | PNG |  |  | Continue developing a macroeconomic and fiscal framework. |  | Claus Iris |  |  |  | 2017-10-23 | 2017-10-27 | 5
Samoa | WSM |  |  | Develop the Samoa Economic and Revenue Forecasting (SERF) Model to undertake debt sustainability analysis and monitor cash and foreign reserves. |  | Claus Iris |  |  |  | 2017-07-03 | 2017-07-07 | 5
Samoa | WSM | 511081 | 531 | Facilitate a cross institution (Ministry of Finance, Ministry for Revenue, Central Bank of Samoa, Samoa Bureau of Statistics) workshop on forecasting and sharing data. | P | Claus Iris |  | 727818 | APD | 2018-04-23 | 2018-04-27 | 5 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Samoa | WSM | 18APY4000 | 510 | Develop GDP forecasting methodology. | P | EXPERT |  |  | APD | 2018-04-08 | 2018-04-28 | 21 | 21 | 0 | PT | MAC_PFT_2017_05 | STX_DELIVERY
Solomon Islands | SLB | 509620 | 531 | Develop the Solomon Islands financial programming frameworks to undertake debt sustainability and external vulnerability assessments. | P | Claus Iris |  | 727818 | APD | 2017-09-18 | 2017-09-22 | 5 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Solomon Islands | SLB | 496106 | 531 | Develop the Solomon Islands financial programming frameworks to undertake debt sustainability and external vulnerability assessments. | P | Claus Iris |  | 727818 | APD | 2018-02-26 | 2018-03-02 | 5 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Tonga | TON | 507429 | 531 | Support the use of the Tonga macroeconomic programming framework. | P | Claus Iris |  | 727818 | APD | 2018-03-19 | 2018-03-23 | 5 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Tuvalu | TUV |  |  | Develop GDP forecasting methodology. |  | Claus Iris |  |  |  | 2017-07-24 | 2017-07-28 | 5
Vanuatu | VUT | 510351 | 531 | Support the use of the national framework for revenue forecasting in budget preparations and the Model of the Vanuatu Economy (MOVE) to produce economic projections. | P | Claus Iris |  | 727818 | APD | 2017-08-14 | 2017-08-18 | 5 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
Vanuatu | VUT | 510716 | 531 | Quantify the price and inflation effects of import duty reductions. | P | Claus Iris |  | 727818 | APD | 2018-01-22 | 2018-01-26 | 5 | 7 | 0 | PT | MAC_PFT_2017_05 | LTX_DELIVERY
PFTAC-Pacific Finan'l Tech Ass | FJI |  |  | Support and advise on econometric estimations, including of a measure of the output gap, and empirical analysis. |  | Claus Iris |  |  |  | 2018-04-16 | 2018-04-20 | 5
PFTAC-Pacific Finan'l Tech Ass | FJI |  |  | Support and advise on econometric estimations, including of a measure of the output gap, and empirical analysis. |  | EXPERT |  |  |  | 2018-04-16 | 2018-04-20 | 5